## Cover Sheet
OPD-INF000A Migration Audit Checklist Template
Revisions Table
Version | Date | Purpose of Revision
1 | 2016-04-06 | Base Document
1.1 | 2016-06-27 | Minor formatting revisions
1.2 | 2016-07-07 | Revised context of questions for clarity; removed unnecessary questions; added numbers column
1.3 | 2022-05-27 | Added definitions tab Added and updated questions Updated the language regarding Contracted Resources/Service Organizations to be consistent with other policies.

## Definitions
Definitions
Service Organization: Third-party vendors, licensors, contractors, or suppliers that provide business or technology solutions and services procured by the Commonwealth
​Contracted Resource: A person whose services, under contract, are provided to the Commonwealth as an independent contractor for a specific purpose and duration. A Contracted Resource is not a Commonwealth employee.
Cloud Service Provider: An entity (private or public) that provides cloud-based platforms, infrastructure, applications, security, and/or storage services for another entity/organization.
​Cloud Use Case Review: An established process to ensure the procurement and/or implementation of any Cloud Computing Service is aligned with the Commonwealth’s overall business and IT vision, strategy, goals, and policies. This process includes representation and review from all domains to pro-actively identify, manage, and mitigate risk, if any, with the Cloud Computing Service being considered. As part of Cloud Use Case Review, the Service Organization (third-party vendor, licensor, contractor, or supplier), is required to complete the Cloud Services Requirements (CSR) document that is specific to the Cloud Computing Service being considered. Any procurement or use of a Cloud Computing Service requires an approved cloud use case.

## Project Plan
# | Project Plan | Yes/No/ NA | Comments
Contract Management Plan
1 | If required, has a Business Proposal (BUS001A) and IT Project Request been submitted and approved in accordance with ITP-BUS001.
2 | If required, has an IT Investment Request been submitted and approved in accordance with ITP-BUS002
3 | Has a Contract Management approach, tools, and project plan been established?
4 | Was the Contract Management plan approved by the Commonwealth? Was the Contract Management plan reviewed with Commonwealth stakeholders?
5 | Were project plans with milestones, deliverables, and schedules determined before the project started?
6 | Are project payments tied into milestones and/or deliverables?
Key Staffing
7 | Are key personnel teams established and documented?
8 | Is the Commonwealth staffing plan approved?
9 | Is a Commonwealth detailed organizational chart created and approved?
10 | Is there Commonwealth staff contingency plan and was it approved?
11 | Is the Service Organization staffing plan approved?
12 | Is a Service Organization detailed organizational chart created and approved?
13 | Were resumes submitted for the key Contracted Resources?
14 | Is there a Contracted Resources contingency plan and was it approved?
Process Manual (PM)
15 | Was a PM created and approved?
16 | Was an Availability and SLA management approach and updates to the PM documented?
17 | Was a change and release management approach or project plan documented?
18 | Was a Service Desk approach, organization, schedule, and project plan documented?
19 | Was a Knowledge/Service Management portal available with contract information, pricing schedules, service offerings, and operating procedures?
20 | Does the PM include: Datacenter Operations, change management, service desk operations, security management, backup management, disaster recovery, performance management, asset management, service level management and configuration management?
21 | Is the PM available on a Knowledge/Service portal?
22 | Was an account management approach and project plan documented?
23 | Was a configuration management approach, tools, and project plan documented?
24 | Was a 3rd party license management approach, tools, and project plan documented?
25 | Was a capacity management approach, tools and project plan documented?
26 | Was a roadmap and project plan created to address the physical or virtual infrastructure: data storage , backups, network connectivity, technical support, staffing, etc.?
27 | Was a Database Management approach, tools, and project plan documented?
28 | Was a Server Capacity on Demand approach, tools, and project plan documented?
29 | Was a Storage Capacity on Demand approach, tools, and project plan documented?
30 | Was an approach, tools, and project plan documented for supporting Limited-Use Colocation Services?
31 | Was there an interim procedure to monitor and manage service delivery including : Problem management, change management, service level monitoring and reporting, physical and logical security, project management, etc. while the service is transitioned from the Commonwealth to the Service Organization?
32 | If moving to a cloud solution was an internal assessment of the Cloud Computing Services requirements listed in ITP-SEC040 completed?
33 | If moving to a cloud solution has a Cloud Use Case (CUC) been submitted and approved?

## Migration Methodology
# | Migration Methodology | Yes/No/ NA | Comments
Migration Methodology - Migration Team
1 | Is a Service Organization Migration Team in place?
2 | Have names and contact information of each Service Organization Migration Team member been established?
3 | Are roles and responsibilities of each Service Organization Migration Team member identified?
4 | Is a Commonwealth Migration Team in place?
5 | Have names and contact information of each Commonwealth Migration Team member been established?
6 | Are roles and responsibilities of each Commonwealth Migration Team member identified?
Migration Methodology - Initiation Phase
7 | Has an initial agency transition meeting been conducted and documented?
8 | Has a scope document agreement been obtained?
9 | Has all documentation relating to the original hardware (i.e.- current diagrams, operational run books, current system /application configurations) been provided?
10 | Has a service catalog order been confirmed and submitted?
Migration Methodology - Planning Phase
11 | Have agency specific architectural designs and diagrams been completed?
12 | Has an application questionnaire been completed?
13 | Have build requirements been agreed to?
Migration Methodology - Execution Phase
14 | Has migration replication been completed?
15 | Has all ordered equipment been received?
16 | For cloud environments, have the virtual servers been defined and made available?
17 | Have all change requests been submitted and approved?
18 | Have systems been provided for post replication testing?
19 | Has testing for all systems been completed?
20 | Have all systems tested been validated for accuracy?
21 | Has agency provided sign off that all applications have been migrated, tested, and successfully validated?
22 | Has a Go/No Go meeting been conducted?
Migration Methodology - Closing Phase
23 | Has lessons learned been conducted?
24 | Has signoff been obtained from vendor operations to hand off environment?
25 | Have all needed approvals to close out wave plan been provided?
26 | Has all documentation been posted to a collaboration site under the specific agency?

## Transition-Conversion Plan
# | Transition-Conversion Plan | Yes/No/ NA | Comments
Detailed Transition Plan
1 | Were all data gathering checklists completed, validated, reviewed, and approved?
2 | Was the data gathering report on a B2B interface to Commonwealth's ITSM system completed?
3 | Was the transition plan approved?
4 | Does the transition plan contain an overall (master) plan?
5 | Does the transition plan contain a plan by Datacenter?
6 | Does the transition plan contain a plan by cloud service provider?
7 | Does the transition plan contain a plan by Agency?
8 | Is there an inventory listing of all infrastructure that needs to be moved for the Agency? Is this listing reviewed and approved by the Agency business process owners?
9 | Does the transition plan contain a plan by Application?
10 | Does the overall, Cloud Service Provider, Datacenter, Agency, and Application transition plans contain the following: transition governance plan, transition risk and mitigation plan, due diligence timeline, configuration/testing verification, and operational readiness?
11 | Was a Transition Management Plan with major milestones created and presented to the Commonwealth for review?
12 | Is there a documented approach to transition Commonwealth computing assets (including roadmap and project plan) to successfully transition the commonwealth using the schedule in the RFP?
13 | Is there a security transition plan?
14 | Was a Data Center Gap Analysis completed?
15 | Was a cloud service provider Gap Analysis completed?
Data Conversion Plan
16 | Is there a data conversion plan to ensure that data is not lost when moving to other infrastructure? This would relate to database servers where the data resides.
17 | Have all records been counted and documented?
18 | Have the pre-migration and post-migration record totals been counted and documented?
19 | Are you testing to ensure that all the data has been migrated successfully?
20 | Does the data conversion plan incorporate the following: methods for collecting, converting and verifying data to be converted, and identifying and resolving any errors found during conversion. This includes comparing the original and converted data for completeness and integrity.
21 | Confirm that the data conversion plan does not require changes in data values unless absolutely necessary for business reasons. Document changes made to data values and secure approval from the business process data owner.
Implementation Plan
22 | Is the project formally defined in the enterprise project management system (i.e. Daptive).
23 | Are all installation and conversion plans signed off by all parties? i.e. Commonwealth, Vendor, Agency, project leaders
24 | Does the installation process for the infrastructure and conversion include: identification of critical/minor systems, support, are they under development, under major modification, need special conditions, etc.?
25 | Does someone review requirements and prerequisites to ensure that they have been fulfilled prior to implementation date?
26 | Does the conversion strategy include: procedures for converting and ensuring correctness of the data after conversion to plan for the approval by the appropriate people, tasks are converting of apps and databases, staffing and org ready for conversion, checking accuracy of converted data, schedule for data conversion, orgs involved and their roles, methods for keeping orgs informed about status
27 | Is there a Master Inventory list of all items required for installation (software, support software, hardware, other)?
28 | Is there a Site Inventory (site software, site support software, site hardware, other inventory, support facilities, training, implementation team)?
29 | Is there a Master and Site listing of physical and access controls needed?
Schedule
30 | Is there an Overall Schedule that provides a high level schedule for all sites, including start and end times for conversion and implementation at each site depicting the required tasks in chronological order?
31 | Does a formal project plan exist?

## Security Plan
# | Security Plan | Yes/No/ NA | Comments
Security
1 | If moving to a cloud solution has a Cloud Use Case Review been completed and approved?
2 | Was a security plan containing architecture, solution, policies and procedures completed and approved?
3 | Is there an approved security management plan?
4 | Is there an approved security and firewall plan?
5 | Are there approved policies and procedures for physical security?
6 | Are there approved policies and procedures for data and network security?
7 | Are there policies and procedures for personnel security (i.e. annual background checks)?
8 | Are there procedures in place for a security assessment to ensure data safety and confidentiality?
9 | Was a Security Management approach, tools, and project plan documented?
10 | Is a Security and Firewall approach, tools and project plan documented?
11 | Was a Baseline Security Risk and Vulnerability Assessment created?
12 | Has a Security Risk and Vulnerability assessment along with roadmap and project plan to address the recommendations identified in the assessment been presented to the Commonwealth?
Equipment/Virtual Infrastructure
13 | For Commonwealth-provided Contracted Resources access to Commonwealth equipment or virtual infrastructure : Are there policies in place to ensure the Contracted Resources access is approved? Policies for Contracted Resources to sign for usage of confidential data? Procedures to monitor Contracted Resource access?
14 | Service Organization has operational responsibility of Commonwealth 3rd party software for which we have valid license and maintenance agreement. Is process in place to document all 3rd party software, valid license and management agreements?
15 | Have any Contracted Resources completed the Acceptable use training and reviewed Management Directive 205.34?
Data Security
16 | The Commonwealth retains administration of logical and data access security: Are procedures in place to administer and monitor logical and data access security?
17 | For Service Organization-hosted Commonwealth security apps (software utilized by the Commonwealth in managing logical and data access security): Does the Service Organization limit access to security apps? Does the Commonwealth monitor Service Organization access to security apps?
18 | Does the Service Organization implement and maintain safeguards against disclosure, destruction, loss or alteration of Commonwealth data?
19 | Does the Service Organization follow federal and state laws, statutes, rules or regulations applicable to data security?
20 | Changes subject to change control process: Is there a change control process in place for logical and data access security?
21 | Service Organization's activities regarding security of data shall be subject to periodic review and monitoring by the Commonwealth or related parties. Does the Commonwealth conduct periodic reviews and monitor the Service Organization's activities regarding security of data?
22 | Does the Service Organization have procedures in place to comply with Federal and State breach laws?
23 | PCI standards if storing credit card data: Are there policy and procedures in place to identify systems that store credit card data? Do these systems require PCI compliance? Are there PCI compliance audit reports?
24 | Does the security plan provide an overview of security considerations associated with installation and or conversion procedures (including changing of default passwords once converted, limiting admin access once converted, which leads to review of security once converted)?
25 | Is encryption being utilized to protect Commonwealth Data in accordance with the standards defined in ITP-SEC031 Encryption Standards and ITP-SEC019 Protection of Commonwealth Data?

## Test Plan
# | Test Plan | Yes/No/ NA | Comments
1 | Are test plans developed to ensure that the application functions in the most efficient manner, users are satisfied with the end results, and the migrated application supports the business processes of the organization?
2 | Do the testing requirements include:
3 | - Functional Testing
4 | - Integration Testing
5 | - Performance Testing
6 | - Volume and Load Stress Testing
7 | - User Acceptance Testing
8 | Is a duplicate environment for initial installation and testing used to ensure that testing will show the same results in both environments?
9 | Are there detailed testing instruction so that each Agency can test their installations the same way in both environments?
10 | Will testing be done in a testing environment that records defects and retests prior to production?

## Change Control
# | Change Control | Yes/No/ NA | Comments
1 | Has a change control system been established and documented?
2 | Are changes approved through a change control board?
3 | Service Organization maintains and upgrades equipment at it's respective end of life or as otherwise required to provide services: Is there a change control process when maintenance and upgrades to equipment are required?
4 | Are changes labeled as critical, high, low, etc.?
5 | Are the changes communicated to all stakeholders?
6 | Are the changes logged?
7 | Are the changes tested prior to implementing?
8 | Are the changes approved prior to implementing?

## Incident, Problem, Defect
# | Incident, Problem, Defect Process | Yes/No/ NA | Comments
ITSM System Integration
1 | Is the integration between the Commonwealth's ITSM system and the vendor ITSM system completed?
2 | Are incidents flowing back and forth between the Commonwealth and the vendor?
3 | Are problems flowing back and forth between the Commonwealth and the vendor?
4 | Are change requests flowing back and forth between the Commonwealth and the vendor?
5 | Are configuration items on both systems reconciled?
6 | Is reporting from vendor's ITSM available to the Commonwealth?
Defect Process
7 | Are defects tracked and recorded?
8 | Are defects labeled with critical, high, low priorities?
9 | Who makes the determination on whether the defects are critical, high, low, etc.?
10 | Have any identified defects been retested prior to implementation?
11 | Are defects resolutions approved prior to implementation?

## Business Continuity
# | Business Continuity | Yes/No/ NA | Comments
Backup and Recovery
1 | Are backup and data recover plans documented throughout the project so that any work performed is continually protected?
2 | Is there a fallback plan in case the transition to new data center or virtual infrastructure does not work?
3 | Is there a plan to keep the old systems available in case of issues with the new systems/infrastructure?
4 | Is there a plan to handle the actual transition and any interruptions to the processing of data?
5 | Is real-time disaster recovery, business continuity and reversion considered in the data conversion and infrastructure migration plan?
6 | Has the disaster recovery plan been tested?
7 | Is there backup of all systems and data taken at a point prior to conversion?
8 | Are audit trails maintained to enable conversion to be retraced?
9 | Is there fallback and recovery plan in case data conversion fails?
10 | Is retention of backup and archived data conformed to business needs and regulatory or compliance requirements?
Archive
11 | Will data be archived? If so, is there a documented plan?

## Cutover
# | Cutover | Yes/No/ NA | Comments
Operational Readiness
1 | Is an Operational Readiness Report completed and accepted when vendor is ready to transition the Commonwealth's applications and services to other datacenters or cloud service providers?
2 | Was a Configuration Item Reconciliation created?
3 | Is a Transition Project Office established and fully staffed?
4 | Is a program plan and architecture developed and approved by the Commonwealth?
5 | Are processes and tools implemented to support the transition change?
6 | Is the datacenter or cloud environment configured, tested, and accepted?
Execution
7 | Completion and acceptance of ALL applications transitioned from the original infrastructure to new infrastructure. Is there a checklist for completion that includes signoffs?
8 | Are high availability, backup, and DR operational for identified systems?
9 | Are Process Manual specific details available in KMP?
10 | Are operations dashboards established to report immediately on status and alerts for transitioned applications?
11 | Are Service Level Agreements identified and are supporting metrics in place?
12 | Is the system operational for scheduling and tracking of ticket-based tasks and incidents?
13 | Does the system collect data to produce configuration, monitoring, and management status reports?
14 | Are DR plans updated and tests scheduled for those systems that have them?
15 | Are there procedures in place for operational support and workloads to be migrated?
16 | Has direct link been severed to the current Datacenter location?
17 | Is there a signoff that all Services provided by vendor have been successfully transitioned?

## New Site Information
# | New Site Information | Yes/No/ NA | Comments
Service Location
1 | Is there a valid and up-to-date list of all datacenter and cloud service provider locations?
2 | Has a new site information detailing site schedule of activities, steps and procedures in the following areas: control input, operating instructions, communications, database description, data conversion, output (including reports), diagnostic messages, restart/recovery procedures been documented?
3 | Has the Commonwealth or the Commonwealth's requested 3rd party, performed on-site inspections, audits, and/or certifications?
4 | Has Service Organization-provided the Commonwealth infrastructure and security specifications in written format for each service location?
5 | The Commonwealth has access to performance records of Service Organization: Does the Commonwealth have access to performance records and how?
6 | Service Organization maintains and enforces environmental and physical security standards and procedures and complies with procedures (Statement of Work): Does the Service Organization have policy and procedures in place to maintain and enforce the stated standards?
7 | Service Organization shall maintain a log recording all entry to any Service Locations, which at all times may be subject to Commonwealth review and audit. Does the Service Organization maintain a log recording all entry to the service locations? Does the Commonwealth have plans to review and monitor the logging of access to service centers?
8 | Service Organizations shall maintain a log recording all entry to any cloud/virtual environments, which at all times may be subject to Commonwealth review and audit. Does the Service Organization maintain a log recording all entry to cloud/virtual environments? Does the Commonwealth have plans to review and monitor the logging of access to cloud/virtual environments?
9 | All security procedures required under contract shall be subject to periodic review by the Commonwealth. Does the Commonwealth have a plan in place to periodically review Service Organization's security procedures?
10 | Does the Service Organization have a plan in place to address security issues when they arise?

## Financial Mgmt
# | Financial Management | Yes/No/ NA | Comments
Financial Management
1 | Is the billing process completed and approved?
2 | Was the billing process tested and implemented and accepted by the Commonwealth?
SSAE 16 Audits
3 | Is there a plan to provide the Commonwealth a SSAE 16 report?
4 | Have results of the SSAE 16 audits been provided when applicable?